## ENSE470_UserStoryMap - Analyst
Activity | Task | Subtask | Subtask description | Status | Estimation | Release | Personas
Analyst Validates Request | Analyst Sign-In with credentials | Credentials given by company |  | Todo |  | First Release: Handle Form and Permissions
Analyst Validates Request | Analyst checks inbox for requests | Requests page with incoming requests |  | Todo |  | First Release: Handle Form and Permissions
Analyst Validates Request | Analyst checks inbox for requests | Detailed view of request |  | Todo |  | First Release: Handle Form and Permissions
Analyst Validates Request | Analyst checks inbox for requests | User request is being processed e-mail |  | Todo |  | Second Release: Notification and Retrieval
Analyst Validates Request | Analyst validates the fields | Analyst able to 'accept' or 'deny' fields = sent back to user |  | Todo |  | Second Release: Notification and Retrieval
Analyst Validates Request | Analyst validates the fields | Resubmit form e-mail |  | Todo |  | Second Release: Notification and Retrieval
Analyst Validates Request | Analyst identifies and assigns the approver | Manual approver selection |  | Todo |  | First Release: Handle Form and Permissions
Analyst Validates Request | Analyst identifies and assigns the approver | Select approver based on company |  | Todo |  | Second Release: Notification and Retrieval
Analyst Validates Request | Analyst identifies and assigns the approver | Retrieve company approvers |  | Todo |  | Second Release: Notification and Retrieval
Analyst Validates Request | Analyst sends request for approvers signature | Send to approver button |  | Todo |  | First Release: Handle Form and Permissions
Analyst Validates Request | Analyst sends request for approvers signature | User request is viewed by approver e-mail |  | Todo |  | Second Release: Notification and Retrieval
Analyst Validates Request | Analyst waits on approver | Awaiting approval page |  | Todo |  | Second Release: Notification and Retrieval
Analyst Validates Request | Analyst notified when request is resolved by approver | Assign permission inbox page |  | Todo |  | First Release: Handle Form and Permissions
Analyst Assigns Permissions | Analyst assigns permission requested if approved | Select permission Click "Confirm" to assign permission |  | Todo |  | First Release: Handle Form and Permissions
Analyst Assigns Permissions | Analyst assigns permission requested if approved | User permissions were approved email |  | Todo |  | Second Release: Notification and Retrieval
Analyst Assigns Permissions | Analyst notifies the user if permission is denied | Denied requests Click "Notice of Denial" or "Notify" |  | Todo |  | Second Release: Notification and Retrieval

## Releases
Name | Is archived
First Release: Handle Form and Permissions | False
Second Release: Notification and Retrieval | False